## Slide 1: What we learnt at DIT while implementing SWAN Scheme in States/UTs

## Slide 2: Process-wise challenges learnt through the implementation of SWANs
DPR/RFP preparation
  Formation of SWAN Committee with at least
    1 or 2 Technical person (Network Expert, as suggested in the approval)
    BSNL representative (to be ensured)
  Identification of PoP Locations ensuring possessions in reasonable period
  Feasibility of the PoP with regards to connectivity
  Technology Assessment
  Finalization of Bill of Material (Vendor Neutrality, Open Standard)
  Site Preparation – Who does? What are the Terms & Conditions?

## Slide 3
Consultant as Technical Assistance provided in the Scheme
  Review of the technology/ architecture/ specifications suggested by the Consultant
  Monitoring the work of consultant as per the Proposed timelines
  Quality of deliverables and the Service Level Agreement Assessment
Process-wise challenges learnt through the implementation of SWANs

## Slide 4: Process-wise challenges learnt through the implementation of SWANs
Bid Process Management
  Bidder response - to be defined clearly
  Vendor interactions - to be minimal and uniform
  Technical team composed for bid evaluation - to have clarity over the requirements of the project and Terms & Conditions defined in RFP
  Evaluation criteria's & “Marking Schema” - to be as objective as possible and to be documented properly before starting of evaluation

## Slide 5: Process-wise challenges learnt through the implementation of SWANs
Network Operator (after LoI)
  Initial Mobilization of resources to meet the commitment (to be ensured)
  Deployment of adequate qualified resources as per the commitment (to be ensured)
  Adherence to the Service Level Agreement during the implementation & operation and proposed timelines

## Slide 6: Process-wise challenges learnt through the implementation of SWANs
Implementation Stage
  Possession of the Sites (almost always delayed)
  BSNL connectivity – State/UT intervention almost inevitable
  Delivery of equipment on time to the respective locations.
  Installation of the equipment and Co-ordination with the State IT Department and BSNL for lease lines
  Preparation of IP Schema keeping State NIC in loop
  Any change in the Bill Of Material (BoM) to be scrutinized and approved very carefully
  Installation of Power and separate meter (nothing happens if State/UT does not intervene)

## Slide 7: Process-wise challenges learnt through the implementation of SWANs
Third Party Auditor (TPA)
  Delay in Identifying TPA although DIT sent the Empanelled list in April 2008
  Clear Identification of Roles and Responsibility and function of TPA
  Deployment of adequate and qualified resources
  TPA report format finalization (has to be vetted by State/UT)
  Format of TPA reporting – to be finalized in consultation with the State/ Consultant/ Network Operator.

## Slide 8: Process-wise challenges learnt through the implementation of SWANs
FAT of Sites
  Installation of all the equipment as per the BOM
  Documentation (to be post-facto audited by TPA agency)
  Inventory Management (to be post-facto audited by TPA agency)
  Inspection of the sites
  All equipment properly configured and operational

## Slide 9: Process-wise challenges learnt through the implementation of SWANs
Operations
  Regular maintenance of equipment including physical & IT
  Periodic review of rules & policy defined for SWAN
  Regular monitoring of bandwidth availability reports generated using SWAN NMS (to ensure CIR by the Bandwidth Service Provider)
  Regular interaction with Bandwidth Service Provider (BSP) to ensure 100% uptime
  Adherence to security policy & guidelines issued by GoI
  Regular State/UT level SWAN Committee meeting (required for financial clearance from DIT)

## Slide 10: Administrative challenges learnt through the implementation of SWANs
Space for Setting up SWAN nodes in Districts and Talukas/ Blocks level offices.
Availability of space for Installation of the Last Mile equipment in the offices.
Ownership of the SWAN by Departments in Districts and Talukas/Blocks.
Provision of Stabilized Uninterrupted Power Supply.
Connecting horizontal offices wherever it is part of SWAN RFP