## Slide 1: Managing People Change

## Slide 2: Overall Change Management Framework
Managing ‘People’ change in e-Governance projects
Capability and Skill Building
Phase I: Establishing Foundation for Change
Phase II: Managing Change
Phase III: Sustaining Change
Assess the environment, scale and scope for change
Define the Change Management Plan
Identify Key Stakeholders
Change Readiness Assessment – Need & Impact
Identify the enablers and disablers to change
Development and Implementation of Communication Strategy
Define performance metrics
Documentation, Monitoring and Evaluation
Corrective Action Plans
Stakeholder Assessment & Engagement Plan
Build the Change Management Team
Conduct Training Needs Analysis
Develop Training Plan

## Slide 3: Overall Change Management Framework
Managing ‘People’ change in e-Governance projects
Phase I: Establishing Foundation for Change
Activities
Assessing the Scale of change in terms of number of affected entities, users, geographical spread, etc.
Assessing the scope in terms of policy, process, system and structure
Assessing the existing environment to understand ‘Change Readiness’ and ‘Culture’ Assessments
Preparing a Change Management Plan
Identifying the key stakeholders, in terms of people impacted and those capable of influencing the outcomes of the change initiatives
Identifying the key enablers and disablers of Change
Establishing Foundation for Change
Managing Change
Sustaining Change

## Slide 4: Overall Change Management Framework
Managing ‘People’ change in e-Governance projects
Phase II: Managing Change
Activities
Assessing the stakeholders for understanding their power, influence, impact and support in the project
Mapping of various stakeholders and stakeholder groups
Building the Change Management Team to make change ‘happen’
Defining the roles and responsibilities of the members of the Change Team
Conducting Training Needs Analysis to understand the training objectives
Prepare the Training Plan for addressing the training needs
Establishing Foundation for Change
Managing Change
Sustaining Change

## Slide 5: Overall Change Management Framework
Managing ‘People’ change in e-Governance projects
Phase III: Sustaining Change
Activities
Identifying the performance metrics for measuring the success of ‘Change’ and cascading the same to the stakeholders
Monitoring and evaluating the metrics to measure the change outcome and incorporate necessary modifications
Developing a repository / knowledgebase for documentation of the ‘Change’
Establishing Foundation for Change
Managing Change
Sustaining Change

## Slide 6: Barriers and success factors related to People
Managing ‘People’ change in e-Governance projects
Top 10 barriers Top 10 success factors
Competing resources 48%
Functional boundaries 44%
Change skills 43%
Middle management 38%
Long IT lead times 35%
Communication 35%
Employee opposition 33%
HR (people/training) issues 33%
Initiative fatigue 32%
Unrealistic timetables 31%
Line manager sponsorship 82%
Treating people fairly 82%
Involving employees 75%
Giving quality communications 70%
Providing sufficient training 68%
Using clear performance measures 65%
Building teams after change 62%
Focusing on culture/skill changes 62%
Rewarding success 60%
Using internal champions 60%
The mentioned survey findings indicate that most of the barriers as well as success factors relate to PEOPLE, hence the need to manage them

## Slide 7
Let us understand some Change theories to better understand the approach for handling ‘People’ in the change management exercise
Managing ‘People’ change in e-Governance projects
Notes: Unfreezing as a concept entered the change literature early to highlight the observation that the stability of human behavior was based on "quasi- stationary equilibria" supported by a large force field of driving and restraining forces. For change to occur, this force field had to be altered under complex psychological conditions because, as was often noted, just adding a driving force toward change often produced an immediate counterforce to maintain the equilibrium. This observation led to the important insight that the equilibrium could more easily be moved if one could remove restraining forces since there were usually already driving forces in the system. Unfortunately restraining forces were harder to get at because they were often personal psychological defenses or group norms embedded in the organizational or community culture.
The full ramifications of such restraining forces were only understood after decades of frustrating encounters with resistance to change, and only then did we begin to pay attention to the work of cognitive psychologists on perceptual defenses, to what psychoanalysts and the Tavistock group were trying to show us with their work on denial, splitting and projection, and to Argyris's seminal work on defensive routines (e.g. Argyris, 1990; Hirschhorn, 1988). In trying to explain what happened to POWs I was led to the necessity to further "unpack" the concept of unfreezing and to highlight what really goes on there. Unfreezing is basically three processes, each of which has to be present to some degree for readiness and motivation to change to be generated.

## Slide 8: Lewin's Change Management Model
  One of the cornerstone models for understanding organizational change was developed by Kurt Lewin back in the 1950s.
  Unfreezing: a person becomes ready to learn or acquire a new behavior, perhaps by recognizing the ineffectiveness of a current behavior or by learning about the benefits that would accrue if the new behavior were implemented.
  Changing: a trial period during which the person familiarizes him or herself with the new behavior.
  Refreezing: new behavior becomes habitual or ingrained with the individual.
Understanding the Three Stages of Change
Managing ‘People’ change in e-Governance projects
Notes: Unfreezing as a concept entered the change literature early to highlight the observation that the stability of human behavior was based on "quasi- stationary equilibria" supported by a large force field of driving and restraining forces. For change to occur, this force field had to be altered under complex psychological conditions because, as was often noted, just adding a driving force toward change often produced an immediate counterforce to maintain the equilibrium. This observation led to the important insight that the equilibrium could more easily be moved if one could remove restraining forces since there were usually already driving forces in the system. Unfortunately restraining forces were harder to get at because they were often personal psychological defenses or group norms embedded in the organizational or community culture.
The full ramifications of such restraining forces were only understood after decades of frustrating encounters with resistance to change, and only then did we begin to pay attention to the work of cognitive psychologists on perceptual defenses, to what psychoanalysts and the Tavistock group were trying to show us with their work on denial, splitting and projection, and to Argyris's seminal work on defensive routines (e.g. Argyris, 1990; Hirschhorn, 1988). In trying to explain what happened to POWs I was led to the necessity to further "unpack" the concept of unfreezing and to highlight what really goes on there. Unfreezing is basically three processes, each of which has to be present to some degree for readiness and motivation to change to be generated.

## Slide 9: Lewin's Change Management Model
Unfreezing involved breaking the existing status quo
Status Quo
Restraining Forces
Driving Forces
Desired State
Time
Lewin’s Force Field Analysis
Equilibrium could more easily be moved if one could remove restraining forces since there were usually already driving forces in the system
Notes: Unfreezing as a concept entered the change literature early to highlight the observation that the stability of human behavior was based on "quasi- stationary equilibria" supported by a large force field of driving and restraining forces. For change to occur, this force field had to be altered under complex psychological conditions because, as was often noted, just adding a driving force toward change often produced an immediate counterforce to maintain the equilibrium. This observation led to the important insight that the equilibrium could more easily be moved if one could remove restraining forces since there were usually already driving forces in the system. Unfortunately restraining forces were harder to get at because they were often personal psychological defenses or group norms embedded in the organizational or community culture.
The full ramifications of such restraining forces were only understood after decades of frustrating encounters with resistance to change, and only then did we begin to pay attention to the work of cognitive psychologists on perceptual defenses, to what psychoanalysts and the Tavistock group were trying to show us with their work on denial, splitting and projection, and to Argyris's seminal work on defensive routines (e.g. Argyris, 1990; Hirschhorn, 1988). In trying to explain what happened to POWs I was led to the necessity to further "unpack" the concept of unfreezing and to highlight what really goes on there. Unfreezing is basically three processes, each of which has to be present to some degree for readiness and motivation to change to be generated.

## Slide 10: John P Kotter's 'eight steps to successful change'
Kotter's eight step change model:
Managing ‘People’ change in e-Governance projects

## Slide 11: John P Kotter's eight steps to successful change
  Increase urgency - inspire people to move, make objectives real and relevant.
  Build the guiding team - get the right people in place with the right emotional commitment, and the right mix of skills and levels.
  Get the vision right - get the team to establish a simple vision and strategy, focus on emotional and creative aspects necessary to drive service and efficiency.
  Communicate for buy-in - Involve as many people as possible, communicate the essentials, simply, and to appeal and respond to people's needs. De-clutter communications - make technology work for you rather than against.
  Empower action - Remove obstacles, enable constructive feedback and lots of support from leaders - reward and recognise progress and achievements.
  Create short-term wins - Set aims that are easy to achieve - in bite-size chunks. Manageable numbers of initiatives. Finish current stages before starting new ones.
  Don't let up - Foster and encourage determination and persistence - ongoing change - encourage ongoing progress reporting - highlight achieved and future milestones.
  Make change stick - Reinforce the value of successful change via recruitment, promotion, new change leaders. Weave change into culture.
Kotter's eight step change model can be summarised as:

## Slide 12: What is Change Management?
Change management is the process, tools and techniques to manage the people-side of business change to achieve the required business / organisational outcome, and to realize that business change effectively within the social infrastructure of the workplace.
Approach for managing ‘People’ change in e-Governance projects
Notes: Notes to the Instructor:
Ask the participants to define/ give their views on change management before moving to the definition in the slide.

## Slide 13: Phases of Transformation: Journey from caterpillar to butterfly involves different kinds of emotions
Complacency
Denial
Finger Pointing
Emotional Energy
Time
Outburst
Depression
Curiosity
Identification
Excitement
Different emotions that people go through during times of ‘Change’
Notes: Stage 1: As information about this transformational change filters through, most employees feel energised.
They have heard about such things being done in other companies. It is a heady feeling of machismo. This is
the complacency stage; i.e. the euphoria of the ignorant!
Stage 2: Then as the benchmarking process begins revealing deep gaps between the company's assumptions
about the market, its capabilities and performance in comparison to the other players in the market, this
complacency and euphoria give way to rationalisation and denial.
Stage 3: As these layers of rationalisation gradually melt away and the obvious conclusion of mediocrity stares
in people's faces, denial gives way to finger pointing.
Stage 4: As deeper analysis shows that the gaps in capabilities are pervasive and deep rooted; i.e. sales is
bad, manufacturing is super-bad and that purchase enjoys one of the worst reputations in the market, the
outburst from people finally happens.
Stage 5: This is when people finally give in and then give up. The toughest phase to plough through is this.
However, this is also the first sight of the end of this horrible tunnel.
Stage 6: This is when we get to see the first glimpses of exploration in new ideas, of curiosity about change
and the new and a sense of possibility. People realise that not everything is rotten. People start recognising
the good things about the situation.
Stage 7: Curiosity about the future will lead to commitment and the sense of possibility will expand into the
excitement of creation.
Gradually you will notice that the butterfly will begin to emerge and then it will learn to fly!

## Slide 14: Approach to manage transformations
  # 1: Successful transformation requires agility and shared understanding of current and predicted drivers for change
  # 2: Building an effective management team to lead change is important but so is the flexibility of the leader’s personal leadership style
  # 3:The customer should remain central at all points in the transformation process
  # 4: Effective communication requires early and ongoing stakeholder planning and management
  # 5: Making culture change stick is a core ingredient of successful transformations
  # 6: Successful execution is impossible without early baselining of “As is” and development of clear metrics to achieve transformation vision
  # 7: Leaders must ensure business can continue as usual, which often requires more resources than planned
Managing ‘People’ change in e-Governance projects
Notes:   # 1: Successful transformation requires agility and shared understanding of current and predicted drivers for change
  The Leadership/ Top Personnel should invest more time upfront discovering and understanding the drivers influencing the need for major change.
  Agreement on this will help improve communication with key stakeholders.
  It is important to react quickly to external change drivers.
  Top executives should either lead or be actively involved in the strategic change discovery process.
  The overriding objective for all transformations – in the private , government and public sectors – is to improve customer experience.
  The change project has to stay focused on delivering improvements to customers.
  # 2: Building an effective management team to lead change is important but so is the flexibility of the leader’s personal leadership style
  Leaders should be tougher with senior managers and executives who are impeding the transformation.
  Leaders tend to wait too long to remove “blockers” or “non-performers” from their executive teams.
  Many leaders stress the importance of having an executive team that is strong, loyal and experienced
  Leader’s leadership style may need to change at a point in time or for a type of transformation
  # 3:The customer should remain central at all points in the transformation process
  Improving customer service should be an explicit goal of the transformation process
  Empowering employees increases employee and customer engagement
  Design a business model that provides greater flexibility to meet ever-changing customer needs.
  Run industry briefings for customers during the transformation.
  Convey a simple and consistent message to customers during the transformation.
  Do not underestimate the linkage between employee engagement, customer engagement and organisational performance.
  Have a single point of contact for customers where possible, to drive a consistent customer experience.
  # 4: Effective communication requires early and ongoing stakeholder planning and management
  Successful transformations require leaders to ensure that the key sponsors are on board
  Leaders should articulate a strong, clear picture to all stakeholders, paying particular attention to external stakeholders
  Clarity and timeliness are essential to effective communication
  Ambitious deadlines are motivational, but leaders should avoid committing to deadlines that they cannot meet
  # 5: Making culture change stick is a core ingredient of successful transformations
  Develop the capability to embed change into teams. This requires early attention to the development of strong change management skills.
  Develop cultural change so that there is a pull towards it, rather than an agenda that has to be pushed.
  Maintain a strong focus on employee values.
  Closely monitor the effects of culture change on the workforce throughout the transformation process.
  # 6: Successful execution is impossible without early baselining of “As is” and development of clear metrics to achieve transformation vision
  There is a need for speed. The first few days are critical for delivering communications and some quick wins.
  Leaders should get the right metrics in place and manage them. They can be simplified to help manage and drive the business.
  # 7: Leaders must ensure business can continue as usual, which often requires more resources than planned
  Leaders need to budget for and plan for extra resources – both internal and external – to ensure the business functions efficiently.
  There should be a clear distinction between business-as-usual initiatives versus transformational initiatives.
  Leaders should find a way provide a more stable environment upon which a transformation team can be based.
  In the initial stage of a transformation, leaders should create a separate group to help develop strategy.

## Slide 15: Managing ‘People’ during times of Change
  Stakeholder Management
  It is a long-term commitment, which spans all through the Change Management effort, and consists of:
  Identifying stakeholders
  Understanding their expectations
  Managing those expectations
  Monitoring the effectiveness of stakeholder engagement activities
  Continuous review of the stakeholder community
  Why is stakeholder management important?
  Getting the stakeholder buy-in is the first step towards laying a strong foundation for ‘Change’
  Identification of key stakeholders is critical for owning and managing the new system and ways of work
  Efficient stakeholder management helps minimise the resistance to change

## Slide 16: Understanding the Key stakeholders
Some of the key stakeholders in an e-Governance Project are:
Individuals such as Secretaries, Head of Ministries, Heads of Directorates;
Project sponsor, Project manager, Heads of budgeting and spending units in pilot
Ministries; Business process owners; Funding Agencies
Consultants, Vendor/ Intermediaries
Divisions, departments or units, employees, user groups, legal entities, or location /
geography (e.g., headquarters, plant, location, state, country), citizens
All these stakeholders can perceive the same project in different ways depending
upon their Expectations
Building a Change Team
Who are the key stakeholders?

## Slide 17: Assessing the Key stakeholders
Stakeholder assessment defines the power, influence, impact on the project and support required from the stakeholders and stakeholder groups.
Influence
Power
Role
Impact
Actions
Level of Support
Stakeholder Assessment
The role of each stakeholder or stakeholder group
Actions to be initiated post stakeholder assessment
The power of each stakeholder or stakeholder group;
The influence of each stakeholder or stakeholder group
The impact of the project on each stakeholder or stakeholder group
The level of support required by each stakeholder or stakeholder group

## Slide 18: Stakeholder Mapping
A stakeholder map tells us:
Who stands to gain and lose from the proposed changes
The main forces and individuals supporting and resisting
The degree of expectation and readiness for change
What factors affect people’s commitment to the process
Possible actions to take, and issues to address

## Slide 19: Understanding the Key stakeholders
Primarily four dimensions need to be considered for understanding the stakeholders:
How powerful and influential the stakeholder is: Low, Medium or High
What would be the impact of change on the stakeholder: Low, Medium or High
What will be the stakeholder’s reaction to change?
  Will he be ‘unsure’ of the change? Low
  Will he just ‘let the change’ happen? Medium
  Will he ‘make the change’ happen? High
  To what extent will the stakeholder support the change? Low, Medium, High

## Slide 20: Stakeholder Engagement in e-Governance projects
Determine the level and type of stakeholder activities required to inform, involve and engage with them.
Invest the appropriate resources to engage with stakeholders who are ‘critical’
Make sure that the Stakeholders are aware of their roles and responsibilities in ensuring success e.g., ICT implementation, the identification and acceptance of the responsibility for owning and managing the day-to-day aspects of the system and the new ways of working
Minimize resistance to the programme through stakeholder engagement
strategies and prevent the programme from being derailed
Build a vision & desire for success of the programme & generate enthusiasm for the change
Notes: Stakeholder management activities in an e-Governance project should begin at the
onset of the project
Continue throughout the project’s life and then continue as part of the post implementation
benefits realisation process.

## Slide 21: Approach to address people related challenges in Change Management
Some steps for managing people related challenges:
Change needs to be explained to people as early as possible
Obtaining people's involvement in validating and refining the changes is crucial
Participation, involvement and open, early, full communication are the important factors.
Workshops are useful processes to develop collective understanding, approaches, policies, methods, systems, ideas, etc.
Staff surveys are a helpful way to repair damage and mistrust among staff, if carried out anonymously, and the results published and acted upon
Management training, empathy and facilitative capability are priority areas
Managing ‘People’ change in e-Governance projects

## Slide 22
What have been the key learning from this session?
Managing ‘People’ change in e-Governance projects
Notes: Notes to the Instructor:
Invite participants to share their key learnings from the session.